## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-001 | I collected user and product data from Olist e-commerce datasets so that I can prepare data for model training | Must Have | None | Data Engineer | Completed
1 | 1 | US-002 | I merged orders, order items, customers, and products datasets so that I have a unified transaction dataset | Must Have | US-001 | Data Engineer | Completed
1 | 1 | US-003 | I handled missing values and duplicates so that my dataset is clean and reliable | Must Have | US-002 | Data Engineer | Completed
1 | 1 | US-004 | I created a user-item interaction matrix so that I can feed it to recommendation algorithms | Must Have | US-003 | Data Engineer | Completed
1 | 1 | US-005 | I filtered users and items with at least 2 interactions so that I avoid cold-start problems | Should Have | US-004 | Data Engineer | Completed
2 | 2 | US-006 | I selected an appropriate recommendation algorithm (SVD) so that I can build collaborative filtering model | Must Have | US-005 | ML Engineer | Completed
2 | 2 | US-007 | I implemented the SVD model using Surprise library so that I have a working recommendation system | Must Have | US-006 | ML Engineer | Completed
2 | 2 | US-008 | I splitted data into training and testing sets so that I can validate model performance | Must Have | US-006 | ML Engineer | Completed
2 | 2 | US-009 | I trained the SVD model with initial hyperparameters so that I establish a baseline performance | Must Have | US-007 | ML Engineer | Completed
2 | 2 | US-010 | I created a recommendation function so that I can generate top-N product suggestions for any user | Must Have | US-009 | ML Engineer | Completed
3 | 3 | US-011 | I implemented precision@k metric so that I can measure recommendation accuracy | Must Have | US-010 | ML Engineer | Completed
3 | 3 | US-012 | I implemented recall@k metric so that I can measure recommendation coverage | Must Have | US-010 | ML Engineer | Completed
3 | 3 | US-013 | I calculated F1-score so that I have a balanced evaluation metric | Must Have | US-011,US-012 | ML Engineer | Completed
3 | 3 | US-014 | I performed hyperparameter tuning (n_factors, n_epochs, learning rate) so that I improve model performance | Must Have | US-013 | ML Engineer | Completed
3 | 3 | US-015 | I compared baseline and refined models so that I validate improvement in metrics | Should Have | US-014 | ML Engineer | Completed
3 | 3 | US-016 | I enhanced recommendation function to include predicted scores so that users see confidence levels | Should Have | US-014 | ML Engineer | Completed
4 | 4 | US-017 | As a developer, I want to design a user-friendly web interface so that users can interact with the recommendation system | Must Have | US-016 | Full Stack Dev | Completed
4 | 4 | US-018 | I created an input form for user selection so that users can get personalized recommendations | Must Have | US-017 | Full Stack Dev | Completed
4 | 4 | US-019 | I integrated the trained SVD model with backend API so that recommendations are generated dynamically | Must Have | US-018 | Backend Dev | Completed
4 | 4 | US-020 | I displayed recommended products with categories so that recommendations are more informative | Should Have | US-019 | Frontend Dev | Completed
4 | 4 | US-021 | I deployed the application on a cloud platform so that it is accessible to users | Must Have | US-019 | DevOps Engineer | Completed
4 | 4 | US-022 | I performed end-to-end testing with multiple user scenarios so that the app works reliably | Must Have | US-021 | QA Engineer | Completed
4 | 4 | US-023 | I implemented error handling and logging so that issues can be debugged efficiently | Should Have | US-019 | Backend Dev | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 218 | 16 | 20 | 23 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Load Olist datasets (orders, order_items, customers, products) using pandas | 2026-01-01 | 2026-01-01 | Jahnavi | Development | Completed | 4 | Day 1: 2; Day 2: 2; Day 3: 0; Day 4: 0; Day 5: 0
US-002 | T-002 | Merge datasets on order_id and customer_id to create unified transaction data | 2026-01-02 | 2026-01-02 | Jahnavi | Development | Completed | 6 | Day 1: 0; Day 2: 3; Day 3: 3; Day 4: 0; Day 5: 0
US-002 | T-003 | Extract relevant columns: customer_unique_id, product_id, category, price, etc. | 2026-01-02 | 2026-01-03 | Jahnavi | Development | Completed | 4 | Day 1: 0; Day 2: 2; Day 3: 2; Day 4: 0; Day 5: 0
US-003 | T-004 | Identify and analyze null values in transaction dataset | 2026-01-03 | 2026-01-03 | Jahnavi | Analysis | Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 3; Day 4: 0; Day 5: 0
US-003 | T-005 | Remove rows with missing critical values (customer_id, product_id) | 2026-01-04 | 2026-01-04 | Jahnavi | Development | Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 4; Day 5: 0
US-003 | T-006 | Identify and remove duplicate transaction records | 2026-01-04 | 2026-01-05 | Jahnavi | Development | Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 2; Day 5: 1
US-004 | T-007 | Create implicit feedback matrix with interaction values | 2026-01-05 | 2026-01-06 | Jahnavi | Development | Completed | 8 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 4
US-004 | T-008 | Aggregate purchase counts per user-item pair | 2026-01-06 | 2026-01-06 | Jahnavi | Development | Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-005 | T-009 | Filter users with minimum 2 interactions to avoid cold-start | 2026-01-06 | 2026-01-07 | Jahnavi | Development | Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-005 | T-010 | Filter items with minimum 2 interactions | 2026-01-07 | 2026-01-07 | Jahnavi | Development | Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-005 | T-011 | Save cleaned dataset to CSV for model training | 2026-01-07 | 2026-01-08 | Jahnavi | Development | Completed | 2 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-006 | T-012 | Research and select SVD algorithm for collaborative filtering | 2026-01-09 | 2026-01-09 | Jahnavi | Research | Completed | 4 | Day 1: 4; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-006 | T-013 | Install and configure scikit-surprise library | 2026-01-09 | 2026-01-10 | Jahnavi | Setup | Completed | 2 | Day 1: 1; Day 2: 1; Day 3: 0; Day 4: 0; Day 5: 0
US-007 | T-014 | Define Reader and Dataset objects from cleaned CSV | 2026-01-10 | 2026-01-11 | Jahnavi | Development | Completed | 6 | Day 1: 0; Day 2: 3; Day 3: 3; Day 4: 0; Day 5: 0
US-008 | T-015 | Split dataset into 80-20 train-test using train_test_split | 2026-01-11 | 2026-01-11 | Jahnavi | Development | Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 3; Day 4: 0; Day 5: 0
US-009 | T-016 | Initialize SVD model with baseline hyperparameters (n_factors=50, n_epochs=20) | 2026-01-12 | 2026-01-12 | Jahnavi | Development | Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 4; Day 5: 0
US-009 | T-017 | Train SVD model on training set and validate convergence | 2026-01-13 | 2026-01-14 | Jahnavi | Development | Completed | 8 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 4; Day 5: 4
US-009 | T-018 | Calculate RMSE and MAE on test set for baseline performance | 2026-01-14 | 2026-01-15 | Jahnavi | Testing | Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 2
US-010 | T-019 | Implement recommend_products_svd() function to generate top-N predictions | 2026-01-15 | 2026-01-16 | Jahnavi | Development | Completed | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 3
US-010 | T-020 | Test recommendation function with sample users | 2026-01-16 | 2026-01-17 | Jahnavi | Testing | Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-010 | T-021 | Map recommended product IDs to categories for display | 2026-01-17 | 2026-01-18 | Jahnavi | Development | Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-011 | T-022 | Implement precision@k calculation function | 2026-01-19 | 2026-01-20 | Jahnavi | Development | Completed | 6 | Day 1: 3; Day 2: 3; Day 3: 0; Day 4: 0; Day 5: 0
US-012 | T-023 | Implement recall@k calculation function | 2026-01-19 | 2026-01-20 | Jahnavi | Development | Completed | 6 | Day 1: 3; Day 2: 3; Day 3: 0; Day 4: 0; Day 5: 0
US-013 | T-024 | Calculate F1-score from precision and recall | 2026-01-20 | 2026-01-21 | Jahnavi | Development | Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 3; Day 4: 0; Day 5: 0
US-013 | T-025 | Evaluate baseline model: Precision@5, Recall@5, F1@5 | 2026-01-21 | 2026-01-21 | Jahnavi | Testing | Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 2; Day 4: 2; Day 5: 0
US-014 | T-026 | Analyze purchase_count distribution for threshold tuning | 2026-01-22 | 2026-01-22 | Jahnavi | Analysis | Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 3; Day 5: 0
US-014 | T-027 | Tune hyperparameters: increase n_factors to 100, n_epochs to 30 | 2026-01-23 | 2026-01-24 | Jahnavi | Development | Completed | 8 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 4; Day 5: 4
US-014 | T-028 | Retrain refined SVD model with optimized parameters | 2026-01-24 | 2026-01-25 | Jahnavi | Development | 3- Completed | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 3
US-015 | T-029 | Compare refined vs baseline: RMSE, MAE, Precision, Recall, F1 | 2026-01-25 | 2026-01-26 | Jahnavi | Testing | Completed | 5 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 2
US-015 | T-030 | Document performance improvements and insights | 2026-01-26 | 2026-01-27 | Jahnavi | Documentation | Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-016 | T-031 | Modify recommendation function to return (item, score) tuples | 2026-01-27 | 2026-01-27 | Jahnavi | Development | Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-016 | T-032 | Test enhanced recommendations with confidence scores | 2026-01-27 | 2026-01-28 | Jahnavi | Testing | Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-017 | T-033 | Design wireframes for recommendation system UI | 2026-01-29 | 2026-01-30 | Jahnavi | Design | 3- Completed | 6 | Day 1: 3; Day 2: 3; Day 3: 0; Day 4: 0; Day 5: 0
US-017 | T-034 | Create HTML/CSS layout for web interface | 2026-01-30 | 2026-02-01 | Jahnavi | Development | 1- Not Started | 8 | Day 1: 0; Day 2: 0; Day 3: 4; Day 4: 4; Day 5: 0
US-018 | T-035 | Build user input form (user ID selection/entry) | 2026-02-01 | 2026-02-03 | Jahnavi | Development | 3- Completed | 8 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 4
US-019 | T-036 | Create Flask/FastAPI backend with prediction endpoint | 2026-02-02 | 2026-02-04 | Jahnavi | Development | 3- Completed | 10 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-019 | T-037 | Load trained SVD model and implement inference logic | 2026-02-04 | 2026-02-05 | Jahnavi | Development | 2- In Progress | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-020 | T-038 | Design recommendation display component with product cards | 2026-02-05 | 2026-02-06 | Jahnavi | Development | 3- Completed | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-020 | T-039 | Integrate category information in recommendation display | 2026-02-06 | 2026-02-07 | Jahnavi | Development | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-021 | T-040 | Set up cloud deployment environment (Heroku/AWS/Render) | 2026-02-06 | 2026-02-07 | Jahnavi | DevOps | 3- Completed | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-021 | T-041 | Configure application for cloud deployment (requirements.txt, Procfile) | 2026-02-07 | 2026-02-07 | Jahnavi | DevOps | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-021 | T-042 | Deploy application and verify accessibility | 2026-02-08 | 2026-02-08 | Jahnavi | DevOps | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-022 | T-043 | Create test cases for various user scenarios | 2026-02-08 | 2026-02-08 | Jahnavi | Testing | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-022 | T-044 | Perform end-to-end testing of recommendation flow | 2026-02-09 | 2026-02-09 | Jahnavi | Testing | 3- Completed | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-023 | T-045 | Implement error handling for API endpoints | 2026-02-09 | 2026-02-10 | Jahnavi | Development | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US-023 | T-046 | Set up logging for debugging and monitoring | 2026-02-10 | 2026-02-10 | Jahnavi | Development | 3- Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 1 | Dataset loading taking longer than expected due to large file sizes | Optimized data loading with chunking; Resolved
1 | 2 | None | N/A
1 | 3 | Clarification needed on which null values are critical vs non-critical | Team discussion held; Documented critical columns
1 | 4 | None | N/A
1 | 5 | Sparse matrix creation causing memory issues | Switched to CSR sparse matrix format; Resolved
2 | 1 | Surprise library installation conflict with existing numpy version | Updated numpy to compatible version; Resolved
2 | 2 | None | N/A
2 | 3 | Model training slower than expected | Reduced sample size for initial testing; Full training scheduled overnight
2 | 4 | Baseline RMSE higher than literature benchmarks | Team reviewed algorithm parameters; Identified need for hyperparameter tuning in Sprint 3
2 | 5 | None | N/A
3 | 1 | Precision and recall calculations giving unexpected results | Reviewed threshold logic; Fixed threshold parameter
3 | 2 | None | N/A
3 | 3 | Hyperparameter search space too large for grid search | Switched to manual tuning based on literature; Resolved
3 | 4 | Model retraining taking 3+ hours | Reduced dataset temporarily for faster iteration
3 | 5 | None | N/A
4 | 1 | Web framework selection debate (Flask vs FastAPI) | Team consensus on Flask for simplicity; Resolved
4 | 2 | Frontend-backend integration issues with CORS | Configured CORS headers in Flask; Resolved
4 | 3 | Model file size too large for free deployment tier | Exploring model compression options
4 | 4 | User authentication not in original scope | Decided to skip authentication for MVP; Can be added later
4 | 5 | None | N/A

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-01-01 | 2026-01-08 | Jahnavi | Use chunked data loading for large datasets | Stop underestimating data preprocessing time | Daily standups for quick issue resolution | Implemented chunked loading strategy
2 | 1 | 2026-01-01 | 2026-01-08 | Jahnavi | Add more data validation checks early | Stop skipping exploratory data analysis | Thorough null value analysis | Created data quality checklist
3 | 2 | 2026-01-09 | 2026-01-18 | Jahnavi | Research algorithms more thoroughly before implementing | Stop rushing into coding without planning | Modular code structure for easy testing | Allocated dedicated research time
4 | 2 | 2026-01-09 | 2026-01-18 | Jahnavi | Document evaluation metrics clearly | Stop assuming everyone understands metrics | Clear communication of performance benchmarks | Created metrics documentation
5 | 3 | 2026-01-19 | 2026-01-28 | Jahnavi | Implement incremental model saving during training | Stop training without checkpoints | Systematic hyperparameter logging | Added model checkpointing
6 | 3 | 2026-01-19 | 2026-01-28 | Jahnavi | Use automated testing for metric calculations | Stop manual verification of every metric | Unit tests for evaluation functions | Created test suite for metrics
7 | 4 | 2026-01-29 | 2026-02-10 | Jahnavi | Start with simple UI mockups before coding | Stop building UI without user feedback | Iterative design with team review | Implemented design review process